## PlanSummary
Author : Anish Nath
Plan Summary | Task-1 |  |  | Task Breakdown | Name of Tasks | Hour
High Level
| Fully Automated environment setup | 1. Jenkins Contnious Integration Server |  | 1 | Document to Automate | 2
|  | 2. Enviromnemts |  | 2 | Automate test to verify the behaviour | 8
|  | 3. Operating Systems |  | 3 | Automate to Single Command | 4
|  | 4. Infrastructure Automation |  | 4 | Versins the Scripts | 2
|  |  | Chef | 5 | Go continous | 16
ubuntu
| Software List |  |  | Low Level
|  | 1. AWS Lamp Stack |  | 1 | Setup and checkin the Application code | 16
|  | 2. Jenkins or CI |  | 2 | Build | 4
|  | 3. git for repository |  | 3 | Deploy | 4
|  | 4. ruby scripts |  | 4 | Make change to Infrastructure | 8
|  | 5. Puppet |  | 5 | CI | 4
|  | 6. AWS Ops Work with Clound formation |  | 6 | View run job with piplelien
7
| Task 2 - Continuous 24/7 Testing Automation |  |  | AWS Tasks
|  | 1. Cucumber acceptance tests that run against the infrastructure |  | 1 | Create AWS account | 1
|  | 2. CI and target environments |  | 2 | Define Security Group | 1
|  | 3. cucumber-testresult-plugin |  | 3 | Use EC2 basic | 1
|  |  |  | 4 | Use Amazon Route | 2
|  |  |  | 5 | Use S3 | 2
|  |  |  | 6 | Use AWS cloud Formation | 2
CI Tasks
|  |  |  | 1 | setup deveopment Environment | 2
|  |  |  | 2 | Install/configure Jenkins Olugins | 2
|  |  |  | 3 | configure scripted env job | 2
|  |  |  | 4 | configure run scheduld jobs | 2
InfraStuture Automation
|  |  |  | 1 | Cloud Formation Template | 5
|  |  |  | 2 | Integrate Chef with Cloudformation | 8
Testing
|  |  |  | 1 | run infrastructure tests in Cucumber. | 8
|  |  |  | Delivery | Put in the delivery piple line | 4